## Sheet1
Phase | Tasks / Deliverables | Responsible Team | Dependencies | Priority | Quarter
Phase 1: Planning and Architecture | Finalize database schema and select vector database. | Backend & ML Engineers | Input from IT & cloud provider approval | P1 | Q1
Design the API and inference architecture for model deployment.
dentify cloud service providers (e.g., AWS, GCP) for both database and model.
Phase 2: Database Setup and API Prototyping | Deploy relational and vector databases. | Backend Engineers | Database resources provisioned by IT | P0
Set up ETL pipelines for data ingestion.
Create API prototype to expose the model’s prediction capabilities.
Phase 3: Initial Model Training and Versioning | Train and validate the model. | ML Engineers | Dataset cleaned and ready for training | P0
Register the trained model in a model registry (e.g., MLflow).
Create Docker container for the model.
Phase 4: Model Deployment and Database Integration | Deploy the model via Docker/Kubernetes. | Backend & ML Engineers | Final model ready & backend aligned | P1
Connect the model API to the backend system.
Configure the vector database to store and retrieve embeddings.
Phase 5: Testing and Performance Optimization | Conduct load testing on the database and model API. | QA & DevOps Team | Monitoring tools in place | P1 | Q2
Optimize query performance with database indexing.
Monitor API latency and tune model inference speed.
Phase 6: CI/CD Integration and Monitoring Setup | Set up CI/CD pipelines for automated model deployment. | DevOps Team | CI/CD tools (e.g., Jenkins) configured | P2
Implement health checks for both database and API uptime monitoring.
Ensure model versioning and rollback mechanisms are available.
Phase 7: User Testing and Feedback Loop | Conduct user testing on the integrated system. | Product & QA Team | Real data and user scenarios available | P3
Implement a feedback mechanism to monitor the accuracy of predictions and data retrieval.
Identify areas for improvement based on user feedback.
Phase 8: Final Rollout and Continuous Improvement | Roll out the final version to production. | All Teams | Live environment prepared | P2
Monitor the system for uptime and accuracy metrics.
Begin identifying monthly performance improvements based on monitoring data.